## Trang_tính1
CAPSTONE 2 : JS FRUITS VALLEY
STT | Task Name | Start Build | Finish Build | %Build | Names Dev | Start Testing | Finish Testing | % Testing | Names Dev | Notes
1 | Layout Header, Carousel (Home page) | 19/01/2024 | 19/01/2024 | 100% | NGUYỄN THỊ BÉ NGOAN | 20/01/2024 | 21/01/2024 | 100% | NGUYỄN THỊ BÉ NGOAN | Completed
2 | Layout Product, Footer (Home page) | 19/01/2024 | 19/01/2024 | 100% | NGUYỄN CÔNG MINH | 19/01/2024 | 19/01/2024 | 100% | NGUYỄN CÔNG MINH | Completed
3 | Layout Cart (Home page) | 20/01/2024 | 20/01/2024 | 100% | NGUYỄN CÔNG MINH | 20/01/2024 | 20/01/2024 | 100% | NGUYỄN CÔNG MINH | Completed
4 | Tính năng Home Page và Giỏ hàng | 20/01/2024 | 25/01/2024 | 100% | NGUYỄN CÔNG MINH | 26/01/2024 | 26/01/2024 | 100% | NGUYỄN CÔNG MINH | Completed
5 | Trang Admin quản lí sản phẩm | 21/01/2024 | 22/01/2024 | 100% | NGUYỄN THỊ BÉ NGOAN | 23/01/2024 | 26/01/2024 | 100% | NGUYỄN THỊ BÉ NGOAN | Completed